## Farm Bot
✅ Farm Bot Project – Updated Task Checklist
Phase | Task | Description | Status
1. Understanding the Project | Study Problem & Purpose | Understand farming issues and prepare a note.
| Research Existing Farm Robots | List features, pros, cons of existing robots.
| Study Farm Bot Functions | Digging, planting, watering, sensors, fire system, arm.
2. Component Study & Documentation | Learn Components | Study ESP32, drivers, motors, sensors, battery.
| Group Component Documentation | Each group creates a datasheet booklet.
| Learn Tools (IDE/Tinkercad) | Install Arduino IDE, create Tinkercad account, test basics.
3. Mechanical Design & Fabrication | Chassis Design | Sketch top/side/bottom view with motor placements.
| 3D Modeling | Design arm joints, dispensers, mounts, holders.
| Mechanical Assembly | Build chassis, mount motors, wheels, 3D parts.
4. Circuit Designing (New Phase Added) | Circuit Planning | Identify all required connections (motors, sensors, ESP32, power).
| Block Diagram Creation | Draw input-output functional block diagram of system.
| Complete Circuit Schematic | Make a clean wiring schematic using Tinkercad/Proteus/Eagle.
| Verify Circuit Logic | Check voltage levels, ground connections, driver compatibility.
| Simulation (Optional) | Test motor, sensor, and servo simulation in Tinkercad if possible.
5. Electronic Assembly | Power Wiring | Connect battery, voltage regulators, switch, fuse.
| Motor & Servo Wiring | Connect DC motors, PCA9685, pump, cutting motor.
| Sensor Wiring | Connect soil moisture, DHT11/22, flame sensor.
| Cross-check With Schematic | Ensure wiring matches the circuit diagram.
6. Programming | ESP32 Setup | Test sensors, motors, servos individually.
| Soil Digging Program | Motor control for digger tool.
| Seed Planting Program | Servo-based seed dropping control.
| Watering Program | Moisture sensor → pump ON/OFF automation.
| Environmental Monitoring | Read temperature & humidity (DHT sensor).
| Fire Detection System | Trigger water nozzle on flame detection.
| Crop Cutting Program | Cutting motor speed + robotic arm control.
7. Integration & Testing | Module Integration | Combine all codes into one main program.
| Field Testing | Test digging, watering, seed planting, fire safety, etc.
| Troubleshooting | Fix mechanical, wiring, and code issues.
8. Documentation & Presentation | Final Project Report | Full documentation with images & diagrams.
| PPT Preparation | 10–12 slide project presentation.
| Live Demonstration | Show all functions working in real environment.
Controling Interface | Mobile App Control | Wi-Fi or Bluetooth control interface.
✅ Farm Bot – Future Plan (Simplified Table)
Future Feature | Description | Priority | Status
AI & Camera Vision | Detect weeds, pests, and crop health using image recognition and machine learning. | High
GPS-Based Navigation | Add autonomous navigation with GPS-based field path planning. | High
Automatic Crop Health Analysis | Use AI models to analyze crop growth, dryness, and disease patterns. | Medium
Solar-Powered Charging | Integrate solar panels for extended battery life and field operation. | Medium
Multi-Robot Coordination | Enable multiple Farm Bots to work together across large farms. | Low

## Rovering Robotic Arm
✅ Rovering Robotic Arm – Complete Task Checklist Table
Phase | Task | Description | Status
1. Understanding the Project | Study Problem & Purpose | Understand cleaning, object handling, mobility challenges.
| Research Existing Assistive Robots | Compare models, features, limitations.
| Study Robot Functions | Walking mechanism, gripper, scrubbing, spraying, wiping.
2. Component Study & Documentation | Component Research | Study ESP32/Arduino, drivers, motors, pump, sensors.
| Create Component Datasheet Booklet | Groups document their assigned components.
| Learn Tools (IDE/Tinkercad) | Install Arduino IDE, test sample codes (LED, motor).
3. Mechanical Design & Fabrication | Frame & Joint Design | Sketch mechanical layout: joints, wheels (optional), arm.
| 3D Modeling (if needed) | Design gripper, scrubber holder, sensor mount, brackets.
| Mechanical Assembly | Build frame, fix motors, mount arm, attach scrubber/wiper.
4. Circuit Designing (Full Phase) | Circuit Planning | Identify power distribution, motor/servo control lines.
| Block Diagram | Draw system overview: inputs → controller → outputs.
| Full Circuit Schematic | Design wiring diagram using Tinkercad/Proteus/Eagle.
| Validate Circuit | Check voltage levels, grounds, driver compatibility.
| Circuit Simulation (Optional) | Test motors, IR sensor, servos virtually.
5. Electronic Assembly | Power Wiring | 12V → motors/pump, 5V → ESP32, servos, IR sensor.
| Motor/Servo Wiring | Connect 4 rover motors, scrubber motor, PCA9685 (optional).
| Pump & Wiper Wiring | Connect pump and wiper mechanism.
| IR Sensor Wiring | Connect obstacle detection sensor.
| Cross-check Wiring | Ensure it matches the designed circuit schematic.
6. Programming | Controller Setup | Test ESP32/Arduino code for motors & sensors.
| Rover Walking Program | Control 4 motors for forward, backward, turning.
| Gripper & Arm Control Program | Servo angles for grabbing, lifting, pushing/pulling.
| Scrubber Motor Program | ON/OFF speed control for cleaning motor.
| Water Pump Program | Control pump for water spray.
| Wiper Mechanism Program | Control wiper motion for cleaning wet surfaces.
| IR Obstacle Detection | Sensor reading + stop/avoid reaction.
| Wireless Control Interface | Bluetooth/Wi-Fi control via app or remote.
7. Integration & Testing | Module Integration | Combine all functions into single master code.
| Mobility Testing | Check walking stability, turning radius.
| Object Handling Test | Gripping, lifting, pushing, pulling.
| Cleaning System Test | Scrubber, pump, wiper performance.
| Sensor Test | IR obstacle detection accuracy.
| Troubleshooting | Fix wiring issues, power load, servo angles.
8. Documentation & Presentation | Final Report | Full documentation with images, diagrams, code.
| PPT Presentation | 10–12 slide project presentation.
| Live Demonstration | Demonstrate walking, gripping, cleaning, spraying, detection.
Future Planning
Optional (Advanced) | Camera Vision | Use camera module for object recognition or navigation.
| Voice/Gesture Control | Control robot using speech or gesture commands.
| High-Torque Upgrade | Use heavy-duty motors for better load handling.
| Water Recycling System | Build eco-friendly cleaning loop.
| AI Autonomous Mode | Add AI path planning, sensing, navigation.